## Project Action Plan Template
Action Plan Template
Project Name: SAMPLE PROJECT 1
Project Goals
Project Goal: Develop a responsive, user-friendly website that enhances brand visibility, improves user engagement, and increases conversions.
Project Objectives
Objective #1: Establish an online presence within 3 months.
Objective #2: Achieve a 10% increase in organic traffic within 6 months of launch
Objective #3: Improve customer interaction and inquiries by 20% within 4 months post-launch
Action Step #1: Market research | [5 empty] | Timeline |  |  | Resources
Priority | Task (Action Item) | Key Performance Indicators (KPIs) | Phase | Assigned | Status | Start Date | Due Date | Duration | Department | Resource requirements | Estimated Cost | Notes
High | Hire Digital Marketing specialist | n/a | Planning | Sam H. | 50% | 2025-02-17 | 2025-02-28 | 2 weeks | HR | HR management team | 5000
High | Gather data | Number of competitors analyzed | Planning | Sam H. | 50% | 2025-02-18 | 2025-03-01 | 2 weeks | Marketing | SEO tools, marketing software | 1500
Medium | Market segmentation | Depth of audience research | Planning | Ada L. | 75% | 2025-02-19 | 2025-03-02 | 2 weeks | Marketing | Customer feedback surveys | 500
Low | Buyer personas brainstorm | n/a | Planning | John G., Helena H., Fred P. | 25% | 2025-02-20 | 2025-03-03 | 2 weeks | Marketing | Marketing team members | 0
Action Step #2: Design site | [5 empty] | Timeline |  |  | Resources
Priority | Task (Action Item) | Key Performance Indicators (KPIs) | Phase | Assigned | Status | Start Date | Due Date | Duration | Department | Resource requirements | Estimated Cost | Notes
High | Create site architecture | Mobile and browser compatibility checks passed | Planning | Sam H. | 50% | 2025-03-10 | 2025-04-21 | 6 weeks | Web Development | Web development software | 2500
High | Design the site's UI | Number of pages designed and developed | Planning | Sam H. | 50% | 2025-03-10 | 2025-04-21 | 6 weeks | Web Development | Web development software | 5000
Medium | Draft content | Number of pages designed and developed | Planning | Ada L. | 75% | 2025-03-10 | 2025-04-21 | 6 weeks | Marketing | Marketing team members | 0
Low | Create images | Number of pages designed and developed | Planning | John G., Helena H., Fred P. | 25% | 2025-03-10 | 2025-04-21 | 6 weeks | Marketing | Graphic design software | 1500
Action Step #3: Launch site | [5 empty] | Timeline |  |  | Resources
Priority | Task (Action Item) | Key Performance Indicators (KPIs) | Phase | Assigned | Status | Start Date | Due Date | Duration | Department | Resource requirements | Estimated Cost | Notes
High | Test site | Load time under 3 seconds | Execution | Sam H. | 50% | 2025-04-24 | 2025-04-28 | 1 week | Web Development | Web content management system | $
Medium | SEO Work | keyword list and SEO strategy prepared | Execution | Ada L. | 75% | 2025-04-24 | 2025-04-28 | 1 week | Marketing | SEO software | 1500
Low | Create new pages | Number of pages designed and developed | Execution | John G., Helena H., Fred P. | 25% | n/a | n/a | Ongoing effort | Marketing | Web content management system | 1500
Low | Monitor site's health | Website traffic, Monthly traffic growth | Execution | John G., Helena H., Fred P. | 25% | n/a | n/a | Ongoing effort | Marketing/Web Development | SEO team
Free related templates
Gantt chart template for Excel
Project dashboard template for Excel
Project budget template for Excel

## Corrective Action Plan
Corrective Action Plan Template
Project Name: SAMPLE PROJECT 1
Problem
Root Cause Analysis
Date | Issue Description | Root Cause | Phase | Priority | Status | Solution |  |  | Department | Resource requirements | Estimated Cost | Notes
Corrective Actions
Action Step #1: | [5 empty] | Timeline |  |  | Resources
Priority | Task (Action Item) | Key Performance Indicators (KPIs) | Phase | Assigned | Status | Start Date | Due Date | Duration | Department | Resource requirements | Estimated Cost | Notes
Planning
Planning
Planning
Planning
Action Step #2: | [5 empty] | Timeline |  |  | Resources
Priority | Task (Action Item) | Key Performance Indicators (KPIs) | Phase | Assigned | Status | Start Date | Due Date | Duration | Department | Resource requirements | Estimated Cost | Notes
Action Step #3 | [5 empty] | Timeline |  |  | Resources
Priority | Task (Action Item) | Key Performance Indicators (KPIs) | Phase | Assigned | Status | Start Date | Due Date | Duration | Department | Resource requirements | Estimated Cost | Notes
Free related templates
Gantt chart template for Excel
Project dashboard template for Excel
Project budget template for Excel

## Strategic Action Plan
Strategic Action Plan Template
Project Name: SAMPLE PROJECT 1
Vision Statement
Mission Statement
Strategic Objectives
Action Step #1: | [5 empty] | Timeline |  |  | Resources
Priority | Task (Action Item) | Key Performance Indicators (KPIs) | Phase | Assigned | Status | Start Date | Due Date | Duration | Department | Resource requirements | Estimated Cost | Notes
Planning
Planning
Planning
Planning
Action Step #2: | [5 empty] | Timeline |  |  | Resources
Priority | Task (Action Item) | Key Performance Indicators (KPIs) | Phase | Assigned | Status | Start Date | Due Date | Duration | Department | Resource requirements | Estimated Cost | Notes
Action Step #3 | [5 empty] | Timeline |  |  | Resources
Priority | Task (Action Item) | Key Performance Indicators (KPIs) | Phase | Assigned | Status | Start Date | Due Date | Duration | Department | Resource requirements | Estimated Cost | Notes
Free related templates
Gantt chart template for Excel
Project dashboard template for Excel
Project budget template for Excel

## Contingency Action Plan
Contingency Action Plan Template
Project Name: SAMPLE PROJECT 1
Risk Assessment
Date | Risk Description | Potential Impact | Likelihood | Priority | Status | Triggering Conditions |  |  | Department | Resource requirements | Estimated Cost | Notes
Risk Mitigation Strategies
Action Step #1: | [5 empty] | Timeline |  |  | Resources
Priority | Task (Action Item) | Key Performance Indicators (KPIs) | Phase | Assigned | Status | Start Date | Due Date | Duration | Department | Resource requirements | Estimated Cost | Notes
Action Step #2: | [5 empty] | Timeline |  |  | Resources
Priority | Task (Action Item) | Key Performance Indicators (KPIs) | Phase | Assigned | Status | Start Date | Due Date | Duration | Department | Resource requirements | Estimated Cost | Notes
Action Step #3 | [5 empty] | Timeline |  |  | Resources
Priority | Task (Action Item) | Key Performance Indicators (KPIs) | Phase | Assigned | Status | Start Date | Due Date | Duration | Department | Resource requirements | Estimated Cost | Notes
Free related templates
Gantt chart template for Excel
Project dashboard template for Excel
Project budget template for Excel

## How to Use This Template
Introduction
When you’re making a project, you start with a strategy. The action plan is that document. It outlines all the steps you need to do in order to accomplish your goal. This action plan template from ProjectManager.com has everything you need to start your project off right.
Definition of Terms
Priority: Notes whether the action is high, medium or low concern.
Task: A small action, one of the steps towards meeting a project goal.
Phase: Where you are in the overall course of the project life cycle.
Assigned: Has the task been assigned to a team member? Who?
Status: What is the percentage done?
Start Date: When tast should initiate.
Due Date: When the task must be complete.
Planned Hours: How long the task should take to get done.
Department: Which department is responsible for the task?
Materials Required: The material resources needed for the task.
Cost: Money allowed for task in budget.
Notes: Comments that don’t fall under other categories.